## Summary
Template | Code | Status | Default | Phases | Tasks | Plan days | Gates | Branches
Branch Opening — Client Flow | MR-PMS-CLIENT-FLOW | published | no | 17 | 59 | 237 | 3 | 1

## CLIENT-FLOW phases
# | Key | Phase | SLA days | Department | Tasks | Modules | Runs with | Branch of | Gate | Capture | Exit criteria
1 | p1 | Phase 1 — Property Research & Site Capture | 15 | expansion | 1 | 0 |  |  |  | collection | Properties recorded and one or more shortlisted (typically 10 listed → 4 shortlisted).
2 | p2 | Phase 2 — Site Evaluation | 5 | expansion | 5 | 4 |  |  | Gate 1 — Property Approved | collection | One final property selected and approved with signature.
3 | p3 | Phase 3 — Commercial Closure | 7 | legal | 5 | 6 |  |  | Gate 2 — LOI Approved | collection | LOI approved and lease executed; downstream parallel streams released.
4 | p20 | Phase 4 — Project Planning & Games | 3 | projects | 1 | 0 |  |  |  | single | Games selected, opening date fixed, and the outline budget agreed.
5 | p22 | HR Hiring & Training | 30 | hr | 1 | 0 |  | p20 |  | collection | Every role filled and the team trained on the games this branch is opening with.
6 | p11 | Phase 5 — Design & Drawings | 20 | projects | 2 | 0 | design-vendor |  |  | collection | A front design direction chosen, and all 29 Set 1 drawings approved — which is what releases the BOQ. Set 2 may still be in progress.
7 | p12 | Phase 6 — Vendor & Contractor Panel | 10 | procurement | 1 | 1 | design-vendor |  |  | collection | A team confirmed and a rate agreed for each of the seven categories. Those rate cards are what price the BOQ — a category left unconfirmed produces a BOQ with no rates.
8 | p13 | Phase 7 — BOQ & Budget | 5 | projects | 1 | 0 |  |  |  | collection | All seven BOQs approved, each by its own owner, and the baseline frozen. Every line carries a source of supply, because only "outside procurement" ever becomes a vendor PO.
9 | p21 | Phase 8 — Contracts & Work Orders | 5 | projects | 2 | 0 |  |  |  | collection | A signed contract for every vendor who will be issued a purchase order, each with a completion date and a retention percentage.
10 | p15 | Phase 9 — Purchase Orders & Delivery Tracking | 45 | procurement | 2 | 0 | build-procure |  |  | single | Every purchase order sent and dispatched by its vendor; deliveries and GRNs tracked to closure on the same sheet.
11 | p6 | Phase 10 — Site Execution / Civil Works | 45 | projects | 3 | 11 | build-procure |  |  | collection | Civil and fit-out works complete as per approved drawings and BOQ.
12 | p16 | Phase 11 — Quality Check | 5 | operations | 4 | 0 |  |  |  | collection | QC passed with all mandatory items cleared.
13 | p18 | Phase 12 — Assembly & Installation | 10 | automation | 3 | 0 |  |  |  | collection | All games and systems installed and verified.
14 | p19 | Phase 13 — Testing & Trial Run | 10 | operations | 3 | 0 |  |  |  | collection | All-OK confirmed; trial run report submitted.
15 | p8 | Phase 14 — Readiness Checklist | 10 | operations | 9 | 14 |  |  | Gate 3 — Launch Clearance | collection | All mandatory departmental checklists approved.
16 | p9 | Phase 15 — Branch Opening / Handover | 5 | operations | 12 | 8 |  |  |  | collection | Branch live; handover accepted by Operations.
17 | p10 | Phase 16 — Closure & Delay Analysis | 7 | finance | 4 | 8 |  |  |  | collection | Closure report accepted; project archived but permanently searchable.

## CLIENT-FLOW tasks
Phase | # | Task | Department | Priority | Est. days | Doer | Backup | Checklist
1. Phase 1 — Property Research & Site Capture | 1 | Capture the properties on site | expansion | high | 15 | emp-exp-001, MR-05, emp-exp-001 | MR-05 | 5
2. Phase 2 — Site Evaluation | 1 | Do the Feasibility assessment | expansion | high | 2 | emp-exp-001, MR-05, emp-exp-001 | MR-05 | 3
2. Phase 2 — Site Evaluation | 2 | Do the Financial assessment | finance | high | 2 | emp-fin-001, emp-fin-001 |  | 3
2. Phase 2 — Site Evaluation | 3 | Do the Operational assessment | operations | high | 2 | emp-ops-001, MR-07, emp-ops-001 | MR-07 | 3
2. Phase 2 — Site Evaluation | 4 | Do the Technical assessment | projects | high | 2 | emp-prj-002, MR-04, emp-prj-002 | MR-04 | 4
2. Phase 2 — Site Evaluation | 5 | Select the final property | expansion | critical | 2 | emp-exp-001, MR-05, emp-exp-001 | MR-05 | 3
3. Phase 3 — Commercial Closure | 1 | Issue Letter of Intent (LOI) | legal | high | 2 | emp-leg-001, emp-leg-001 |  | 3
3. Phase 3 — Commercial Closure | 2 | Draft & finalize lease agreement | legal | critical | 3 | emp-leg-001, emp-leg-001 |  | 4
3. Phase 3 — Commercial Closure | 3 | Legal verification & title due diligence | legal | critical | 2 | emp-leg-001, emp-leg-001 |  | 3
3. Phase 3 — Commercial Closure | 4 | Security deposit & token payment | finance | high | 1 | emp-fin-001, emp-fin-001 |  | 3
3. Phase 3 — Commercial Closure | 5 | NOCs & statutory approvals | legal | high | 2 | emp-leg-001, emp-leg-001 |  | 4
4. Phase 4 — Project Planning & Games | 1 | Fill the project plan — games, dates & budget | operations | critical | 2 | emp-ops-001, MR-07, emp-ops-001 | MR-07 | 3
5. HR Hiring & Training | 1 | Hire and train the team for this branch | hr | high | 30 | MR-11, MR-11 |  | 4
6. Phase 5 — Design & Drawings | 1 | Put up the initial front design options | projects | high | 5 | emp-prj-002, MR-04, emp-prj-002 | MR-04 | 5
6. Phase 5 — Design & Drawings | 2 | Create the working drawings for this property | projects | high | 10 | emp-prj-002, MR-04, emp-prj-002 | MR-04 | 3
7. Phase 6 — Vendor & Contractor Panel | 1 | Finalise the vendors for this project | procurement | high | 10 | emp-proc-001, emp-proc-002, emp-proc-001 | emp-proc-002 | 5
8. Phase 7 — BOQ & Budget | 1 | Build the BOQ — one line per thing to buy | projects | critical | 3 | emp-prj-002, MR-04, emp-prj-002 | MR-04 | 3
9. Phase 8 — Contracts & Work Orders | 1 | Draft the work orders from the approved BOQs | projects | critical | 2 | emp-prj-002, MR-04, emp-prj-002 | MR-04 | 4
9. Phase 8 — Contracts & Work Orders | 2 | Sign the contracts with the vendors | projects | critical | 3 | emp-prj-002, MR-04, emp-prj-002 | MR-04 | 3
10. Phase 9 — Purchase Orders & Delivery Tracking | 1 | Send every PO and keep the tracker honest | procurement | critical | 45 | emp-proc-001, emp-proc-002, emp-proc-001 | emp-proc-002 | 4
10. Phase 9 — Purchase Orders & Delivery Tracking | 2 | Receive goods at site and record the GRN | operations | high | 45 | emp-ops-001, MR-07, emp-ops-001 | MR-07 | 3
11. Phase 10 — Site Execution / Civil Works | 1 | Report from site every working day | construction | high | 45 | emp-con-001, MR-09, emp-con-001 | MR-09 | 4
11. Phase 10 — Site Execution / Civil Works | 2 | Start hiring for this centre | hr | high | 12 | MR-11, MR-11 |  | 4
11. Phase 10 — Site Execution / Civil Works | 3 | Get the site technically ready | it | high | 12 | emp-it-001, MR-10, emp-it-001 | MR-10 | 4
12. Phase 11 — Quality Check | 1 | Inspect the site & file QC items | operations | critical | 3 | emp-ops-001, MR-07, emp-ops-001 | MR-07 | 3
12. Phase 11 — Quality Check | 2 | Fix what failed & re-check | construction | critical | 5 | emp-con-001, MR-09, emp-con-001 | MR-09 | 3
12. Phase 11 — Quality Check | 3 | Check hiring is on track | hr | high | 2 | MR-11, MR-11 |  | 2
12. Phase 11 — Quality Check | 4 | Verify the technical setup | it | high | 2 | emp-it-001, MR-10, emp-it-001 | MR-10 | 3
13. Phase 12 — Assembly & Installation | 1 | Install games, props & AV | automation | critical | 10 | emp-aut-001, emp-aut-002, emp-aut-001 | emp-aut-002 | 3
13. Phase 12 — Assembly & Installation | 2 | Install IT, network & systems | it | critical | 5 | emp-it-001, MR-10, emp-it-001 | MR-10 | 4
13. Phase 12 — Assembly & Installation | 3 | Verify every installation | projects | high | 2 | emp-prj-002, MR-04, emp-prj-002 | MR-04 | 2
14. Phase 13 — Testing & Trial Run | 1 | Play & test every game — log every error | operations | critical | 7 | emp-ops-001, MR-07, emp-ops-001 | MR-07 | 3
14. Phase 13 — Testing & Trial Run | 2 | Fix the errors & re-test until All-OK | automation | critical | 5 | emp-aut-001, emp-aut-002, emp-aut-001 | emp-aut-002 | 3
14. Phase 13 — Testing & Trial Run | 3 | Staff readiness & mock run | hr | high | 5 | MR-11, MR-11 |  | 4
15. Phase 14 — Readiness Checklist | 1 | Readiness: Construction | construction | medium | 3 | emp-con-001, MR-09, emp-con-001 | MR-09 | 10
15. Phase 14 — Readiness Checklist | 2 | Readiness: Utilities | construction | critical | 3 | emp-con-001, MR-09, emp-con-001 | MR-09 | 9
15. Phase 14 — Readiness Checklist | 3 | Readiness: It Systems | it | high | 3 | emp-it-001, MR-10, emp-it-001 | MR-10 | 12
15. Phase 14 — Readiness Checklist | 4 | Readiness: Hiring | hr | high | 3 | MR-11, MR-11 |  | 6
15. Phase 14 — Readiness Checklist | 5 | Readiness: Training | hr | high | 3 | MR-11, MR-11 |  | 6
15. Phase 14 — Readiness Checklist | 6 | Readiness: Marketing | marketing | medium | 3 | emp-mkt-001, MR-12, emp-mkt-001 | MR-12 | 10
15. Phase 14 — Readiness Checklist | 7 | Readiness: Testing | operations | critical | 3 | emp-ops-001, MR-07, emp-ops-001 | MR-07 | 8
15. Phase 14 — Readiness Checklist | 8 | Readiness: Inventory | procurement | high | 3 | emp-proc-001, emp-proc-002, emp-proc-001 | emp-proc-002 | 10
15. Phase 14 — Readiness Checklist | 9 | Readiness: Compliance | legal | critical | 3 | emp-leg-001, emp-leg-001 |  | 10
16. Phase 15 — Branch Opening / Handover | 1 | Go-live: Operations | operations | medium | 3 | emp-ops-001, MR-07, emp-ops-001 | MR-07 | 9
16. Phase 15 — Branch Opening / Handover | 2 | Go-live: It | it | high | 3 | emp-it-001, MR-10, emp-it-001 | MR-10 | 5
16. Phase 15 — Branch Opening / Handover | 3 | Go-live: Pos | it | critical | 3 | emp-it-001, MR-10, emp-it-001 | MR-10 | 6
16. Phase 15 — Branch Opening / Handover | 4 | Go-live: Internet | it | critical | 3 | emp-it-001, MR-10, emp-it-001 | MR-10 | 4
16. Phase 15 — Branch Opening / Handover | 5 | Go-live: Power Backup | construction | critical | 3 | emp-con-001, MR-09, emp-con-001 | MR-09 | 4
16. Phase 15 — Branch Opening / Handover | 6 | Go-live: Staff | hr | high | 3 | MR-11, MR-11 |  | 5
16. Phase 15 — Branch Opening / Handover | 7 | Go-live: Security | operations | high | 3 | emp-ops-001, MR-07, emp-ops-001 | MR-07 | 4
16. Phase 15 — Branch Opening / Handover | 8 | Go-live: Emergency Contacts | operations | medium | 3 | emp-ops-001, MR-07, emp-ops-001 | MR-07 | 4
16. Phase 15 — Branch Opening / Handover | 9 | Go-live: Inventory | procurement | high | 3 | emp-proc-001, emp-proc-002, emp-proc-001 | emp-proc-002 | 5
16. Phase 15 — Branch Opening / Handover | 10 | Go-live: Marketing | marketing | high | 3 | emp-mkt-001, MR-12, emp-mkt-001 | MR-12 | 5
16. Phase 15 — Branch Opening / Handover | 11 | Go-live: Legal | legal | critical | 3 | emp-leg-001, emp-leg-001 |  | 5
16. Phase 15 — Branch Opening / Handover | 12 | Go-live: Finance | finance | medium | 3 | emp-fin-001, emp-fin-001 |  | 4
17. Phase 16 — Closure & Delay Analysis | 1 | Budget variance analysis | finance | high | 2 | emp-fin-001, emp-fin-001 |  | 3
17. Phase 16 — Closure & Delay Analysis | 2 | Delay & schedule analysis | projects | medium | 1 | emp-prj-002, MR-04, emp-prj-002 | MR-04 | 2
17. Phase 16 — Closure & Delay Analysis | 3 | Vendor performance review | procurement | medium | 1 | emp-proc-001, emp-proc-002, emp-proc-001 | emp-proc-002 | 2
17. Phase 16 — Closure & Delay Analysis | 4 | Lessons learned documentation | operations | medium | 1 | emp-ops-001, MR-07, emp-ops-001 | MR-07 | 2